## Project Inputs
Burndown Chart
kickoff.pmi.org | Project Name: | Online Book Store System
Project Manager:
How To Use This Worksheet:
Objective | This is a template that can be used to create a burndown chart. This specific template assumes a five day sprint.
What To Complete | All fields where cells are shaded gray. In these cells, first enter the total number of hours needed to complete each task; then, enter the number of hours spent daily on each of the tasks. Do not enter any values in white cells.
Content Requirements | Name | Description
| Actual Effort | This tracks the actual number of hours remaining for the collective tasks in a sprint. This is estimated on a daily basis.
| Ideal Effort | This tracks the ideal/projected number of hours remaining for the collective tasks in a sprint. This is estimated on a daily basis.
| Starting Hours | This indicates the number of hours needed to complete a task before any work is done.
| Task | This indicates the name/title of each task that is being tracked.
| Day | This is the number of hours spent on a given task for the day.
Sprint 1
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day10
Actual Effort (Hours) | 39 | 38 | 37 | 34 | 29 | 24 | 19 | 14 | 6 | 1 | 0
Ideal Effort (Hours) | 39 | 35.1 | 31.2 | 27.3 | 23.4 | 19.5 | 15.6 | 11.7 | 7.8 | 3.9 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Sprint Planning | [11 empty] | 1 | bar: 39 to 35.1
Assign roles & define tasks | [11 empty] | 1 | bar: 39; 31.2
Confirm backend tech stack & DB | 39: 3; 27.3: 3 | 3
Setup API endpoint & DB schema | 39: 5; 23.4: 5 | 5
User Auth API (register/login) | 39: 5; 19.5: 5 | 5
Frontend-backend auth integration | 39: 5; 15.6: 5 | 5
Role-based access control (RBAC) | 39: 5; 11.7: 5 | 5
OAuth/Social Login | 39: 8; 7.8: 8 | 8
Testing, error handling, improvements | 39: 5; 3.9: 5 | 5
Sprint Review & Demo | [11 empty] | 1 | bar: 39; 0
Sprint 2
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day10
Actual Effort (Hours) | 41 | 40 | 37 | 32 | 27 | 22 | 17 | 12 | 4 | 1 | 0
Ideal Effort (Hours) | 41 | 36.9 | 32.8 | 28.7 | 24.6 | 20.5 | 16.4 | 12.3 | 8.2 | 4.1 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Sprint Planning | 1 | [10 empty] | 1 | bar: Day 1
Define listing/search/inventory tasks | 3 | Day 2: 3 | 3
Backend API for book management | 5 | Day 3: 5 | 5
UI for book browsing & search | 5 | Day 4: 5 | 5
CRUD operations for inventory | 5 | Day 5: 5 | 5
Connect frontend with APIs | 5 | Day 6: 5 | 5
Admin approval system | 5 | Day 7: 5 | 5
Search & filtering | 8 | Day 8: 8 | 8
Test browsing/filtering/inventory | 3 | Day 9: 3 | 3
Bug fixes, UI refinement | 1 | [10 empty] | 1 | bar: Day10
Sprint 3
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day10
Actual Effort (Hours) | 39 | 38 | 37 | 32 | 27 | 19 | 14 | 11 | 6 | 5 | 0
Ideal Effort (Hours) | 39 | 35.1 | 31.2 | 27.3 | 23.4 | 19.5 | 15.6 | 11.7 | 7.8 | 3.9 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Sprint Planning | [11 empty] | 1 | bar: 39 to 35.1
Assign cart/order/payment tasks | [11 empty] | 1 | bar: 39; 31.2
Backend API for cart | 39: 5; 27.3: 5 | 5
UI implementation cart/checkout | 39: 5; 23.4: 5 | 5
Backend payment logic | 39: 8; 19.5: 8 | 8
Integrate frontend with payment API | 39: 5; 15.6: 5 | 5
Seller order tracking | 39: 3; 11.7: 3 | 3
Admin monitoring & dispute handling | 39: 5; 7.8: 5 | 5
Bug fixes in checkout/order | [11 empty] | 1 | bar: 39; 3.9
Security testing & fraud detection | 39: 5; 0: 5 | 5
Sprint 4
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day10
Actual Effort (Hours) | 36 | 35 | 32 | 27 | 22 | 17 | 12 | 9 | 4 | 1 | 0
Ideal Effort (Hours) | 36 | 32.4 | 28.8 | 25.2 | 21.6 | 18 | 14.4 | 10.8 | 7.2 | 3.6 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Sprint Planning | 1 | [10 empty] | 1 | bar: Day 1
Define subscription & earnings tracking | 3 | Day 2: 3 | 3
Backend API for subscriptions | 5 | Day 3: 5 | 5
UI for subscription purchase | 5 | Day 4: 5 | 5
Payment for subscriptions | 5 | Day 5: 5 | 5
Earnings dashboard | 5 | Day 6: 5 | 5
Admin panel for commissions | 3 | Day 7: 3 | 3
Subscription tracking & access control | 5 | Day 8: 5 | 5
Testing subscription activation | 3 | Day 9: 3 | 3
Bug fixes & optimization | 1 | [10 empty] | 1 | bar: Day10
Sprint 5
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day10
Actual Effort (Hours) | 37 | 36 | 35 | 30 | 25 | 17 | 14 | 9 | 4 | 3 | 0
Ideal Effort (Hours) | 37 | 33.3 | 29.6 | 25.9 | 22.2 | 18.5 | 14.8 | 11.1 | 7.4 | 3.7 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Sprint Planning | 1 | [10 empty] | 1 | bar: Day 1
Assign tasks for comparison & discounts | 1 | [10 empty] | 1 | bar: Day 2
Backend API for price comparison | 5 | Day 3: 5 | 5
UI for price comparison results | 5 | Day 4: 5 | 5
Discount management system | 8 | Day 5: 8 | 8
Seller UI for managing discounts | 3 | Day 6: 3 | 3
Frontend-backend integration | 5 | Day 7: 5 | 5
Discount validation & logic | 5 | Day 8: 5 | 5
Bug fixes in price calculation | 1 | [10 empty] | 1 | bar: Day 9
UI performance improvements | 3 | Day10: 3 | 3
Sprint Review and Retrospective | 1 | [10 empty] | 1 | bar: Day10
Sprint 6
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day10
Actual Effort (Hours) | 32 | 31 | 26 | 21 | 18 | 13 | 10 | 5 | 4 | 1 | 0
Ideal Effort (Hours) | 32 | 28.8 | 25.6 | 22.4 | 19.2 | 16 | 12.8 | 9.6 | 6.4 | 3.2 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Sprint Planning | 1 | [10 empty] | 1 | bar: Day 1
Design admin panel layout | 5 | Day 2: 5 | 5
Backend API for seller approvals | 5 | Day 3: 5 | 5
Subscription tracking integration | 3 | Day 4: 3 | 3
Sales analytics dashboard | 5 | Day 5: 5 | 5
Dashboard UX improvements | 3 | Day 6: 3 | 3
Secure access controls | 5 | Day 7: 5 | 5
Bug fixes and testing | 1 | [10 empty] | 1 | bar: Day 8
Performance optimization | 3 | Day 9: 3 | 3
Sprint Review | 1 | [10 empty] | 1 | bar: Day10
Sprint 7
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day10
Actual Effort (Hours) | 34 | 33 | 30 | 25 | 20 | 15 | 12 | 9 | 6 | 1 | 0
Ideal Effort (Hours) | 34 | 30.6 | 27.2 | 23.8 | 20.4 | 17 | 13.6 | 10.2 | 6.8 | 3.4 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Sprint Planning | 1 | [10 empty] | 1 | bar: Day 1
UI for review submission & rating | 3 | Day 2: 3 | 3
Backend API for reviews | 5 | Day 3: 5 | 5
Frontend-backend integration | 5 | Day 4: 5 | 5
Verified purchase restrictions | 5 | Day 5: 5 | 5
Enhanced filtering (rating/date) | 3 | Day 6: 3 | 3
Bug fixes: posting, deletion | 3 | Day 7: 3 | 3
Pagination | 3 | Day 8: 3 | 3
UI improvements for review stats | 5 | Day 9: 5 | 5
Sprint Review & Demo | 1 | [10 empty] | 1 | bar: Day10
Sprint 8
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day10
Actual Effort (Hours) | 34 | 33 | 28 | 25 | 20 | 17 | 12 | 9 | 4 | 1 | 0
Ideal Effort (Hours) | 34 | 30.6 | 27.2 | 23.8 | 20.4 | 17 | 13.6 | 10.2 | 6.8 | 3.4 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Sprint Planning | 1 | [10 empty] | 1 | bar: Day 1
API performance testing | 5 | Day 2: 5 | 5
UI/UX refinements | 3 | Day 3: 3 | 3
Security testing | 5 | Day 4: 5 | 5
Fixing security vulnerabilities | 3 | Day 5: 3 | 3
Setup deployment | 5 | Day 6: 5 | 5
DB migration & production testing | 3 | Day 7: 3 | 3
Load testing | 5 | Day 8: 5 | 5
Final deployment checks & polish | 3 | Day 9: 3 | 3
Sprint Review & Go Live | 1 | [10 empty] | 1 | bar: Day10

## Velocity Chart
Sprint | Commitment | Work Completed
Sprint 1 | 41 | 39
Sprint 2 | 42 | 41
Sprint 3 | 41 | 39
Sprint 4 | 38 | 36
Sprint 5 | 38 | 37
Sprint 6 | 35 | 32
Sprint 7 | 34 | 34
Sprint 8 | 35 | 34