## Project Inputs
Burndown Chart
kickoff.pmi.org | Project Name: | Online Book Store System
Project Manager:
How To Use This Worksheet:
Objective | This is a template that can be used to create a burndown chart. This specific template assumes a five day sprint.
What To Complete | All fields where cells are shaded gray. In these cells, first enter the total number of hours needed to complete each task; then, enter the number of hours spent daily on each of the tasks. Do not enter any values in white cells.
Content Requirements | Name | Description
| Actual Effort | This tracks the actual number of hours remaining for the collective tasks in a sprint. This is estimated on a daily basis.
| Ideal Effort | This tracks the ideal/projected number of hours remaining for the collective tasks in a sprint. This is estimated on a daily basis.
| Starting Hours | This indicates the number of hours needed to complete a task before any work is done.
| Task | This indicates the name/title of each task that is being tracked.
| Day | This is the number of hours spent on a given task for the day.
Sprint 1
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Actual Effort (Hours) | 76 | 71 | 61 | 54 | 48 | 41 | 35 | 29 | 18 | 9 | 0
Ideal Effort (Hours) | 76 | 68.4 | 60.8 | 53.2 | 45.6 | 38 | 30.4 | 22.8 | 15.2 | 7.6 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Sprint Planning | 6 | Day 1: 3; Day 2: 3 | 6
Assign team roles & define tasks | 5 | Day 1: 2; Day 2: 3 | 5
Confirm backend tech stack & DB selection | 7 | Day 2: 4; Day 3: 3 | 7
Setup API endpoint & DB schema | 7 | Day 3: 4; Day 4: 3 | 7
User Auth API (register/login) | 6 | Day 4: 3; Day 5: 3 | 6
Frontend-backend authentication integration | 7 | Day 5: 4; Day 6: 3 | 7
Role-based access control (RBAC) | 6 | Day 6: 3; Day 7: 3 | 6
OAuth/Social Login authentication | 7 | Day 7: 3; Day 8: 4 | 7
Testing, error handling & final improvements | 19 | Day 8: 7; Day 9: 6; Day 10: 6 | 19
Sprint Review (Authentication demo) | 6 | Day 9: 3; Day 10: 3 | 6
Sprint 2
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Actual Effort (Hours) | 68 | 62 | 51 | 44 | 37 | 31 | 25 | 17 | 10 | 3 | 0
Ideal Effort (Hours) | 68 | 61.2 | 54.4 | 47.6 | 40.8 | 34 | 27.2 | 20.4 | 13.6 | 6.8 | 1.2434e-14
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Sprint Planning | 6 | Day 1: 3; Day 2: 3 | 6
Define book listing, search, inventory tasks | 7 | Day 1: 3; Day 2: 4 | 7
Backend API development for book management | 8 | Day 2: 4; Day 3: 4 | 8
Frontend UI design for book browsing & search | 7 | Day 3: 3; Day 4: 4 | 7
CRUD operations for book inventory | 6 | Day 4: 3; Day 5: 3 | 6
Connect frontend with APIs | 6 | Day 5: 3; Day 6: 3 | 6
Develop admin approval system for book listings | 7 | Day 6: 3; Day 7: 4 | 7
Implement search & filtering functionality | 7 | Day 7: 4; Day 8: 3 | 7
Test book browsing, filtering, and inventory | 8 | Day 8: 4; Day 9: 4 | 8
Bug fixes, UI refinements, improved API response | 6 | Day 9: 3; Day 10: 3 | 6
Sprint 3
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Actual Effort (Hours) | 67 | 61 | 51 | 43 | 36 | 29 | 23 | 16 | 10 | 3 | 0
Ideal Effort (Hours) | 67 | 60.3 | 53.6 | 46.9 | 40.2 | 33.5 | 26.8 | 20.1 | 13.4 | 6.7 | -1.2434e-14
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Sprint Planning | 6 | Day 1: 3; Day 2: 3 | 6
Assign tasks for order placement, cart, payment | 8 | Day 1: 3; Day 2: 3; Day 3: 2 | 8
Backend API for cart management | 7 | Day 2: 4; Day 3: 3 | 7
UI implementation for cart and checkout flow | 6 | Day 3: 3; Day 4: 3 | 6
Backend payment processing logic | 7 | Day 4: 4; Day 5: 3 | 7
Integrate frontend with payment API | 7 | Day 5: 4; Day 6: 3 | 7
Seller order tracking implementation | 6 | Day 6: 3; Day 7: 3 | 6
Admin order monitoring and dispute handling | 7 | Day 7: 4; Day 8: 3 | 7
Bug fixes in checkout and order flow | 6 | Day 8: 3; Day 9: 3 | 6
Security testing and fraud detection | 7 | Day 9: 4; Day 10: 3 | 7
Sprint 4
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Actual Effort (Hours) | 68 | 62 | 52 | 44 | 37 | 30 | 24 | 17 | 11 | 3 | 0
Ideal Effort (Hours) | 68 | 61.2 | 54.4 | 47.6 | 40.8 | 34 | 27.2 | 20.4 | 13.6 | 6.8 | 1.2434e-14
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total
Sprint Planning | 6 | Day 1: 3; Day 2: 3 | 6
Define subscription packages & earnings | 8 | Day 1: 3; Day 2: 3; Day 3: 2 | 8
Backend API for subscription management | 7 | Day 2: 4; Day 3: 3 | 7
UI design for seller subscription purchase | 6 | Day 3: 3; Day 4: 3 | 6
Integrate payment system for subscription | 7 | Day 4: 4; Day 5: 3 | 7
Implement earnings dashboard for sellers | 7 | Day 5: 4; Day 6: 3 | 7
Admin panel for tracking commissions & payments | 6 | Day 6: 3; Day 7: 3 | 6
Integrated subscription tracking & access control | 7 | Day 7: 4; Day 8: 3 | 7
Testing subscription activation, upgrades/downgrades | 7 | Day 8: 3; Day 9: 4 | 7
Bug fixes, UI refinements, API optimization | 7 | Day 9: 4; Day 10: 3 | 7